## Gantt Chart
GANTT CHART | [6 empty] | Project Deliverables ➜ | [7 empty] | Develop a web-based eCommerce website with AI based products originality verification application
PROJECT TITLE |  | eCommerce website with AI based products originality verification |  |  |  |  | Institutaion Name | [8 empty] | IIIT Hyderabad & Great Learning
PROJECT MANAGER |  | Ashutosh Karol |  |  |  |  | DATE | [8 empty] | 2022-09-25
Front End Team Lead |  | Anita Dash
Back End Team Lead |  | Jophy Joseph
Deployment Team Lead |  | Dipanwnita Banerjee
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE
[7 empty] | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4
[7 empty] | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su
1 | Week -1 |  | 2022-09-25 | 2022-10-01 | 6 | 0%
1.1 | Project Management |  |  |  | 6 | 0%
1.1.1 | Project Architecture(HLD and LLD) | Ashutosh Karol | 2022-09-25 | 2022-10-01 | 6 | 0%
1.1.2 | Week2 tasks recommendation | Ashutosh Karol | 2022-09-25 | 2022-10-01 | 6 | 0%
1.1.3 | Project Documentation |  | 2022-09-25 | 2022-10-23 | 28 | 0%
1.1.4 | Minutes of Meetings - Documentation | Polagani srinath, Fahmaan Mohammed and Vaishnavi Deshay | 2022-09-25 | 2022-10-23 | 28 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
1.2 | Frontend |  |  |  | 6 | 0%
1.2.1. | Front End Architecture (HLD and LLD) | Anita Dash, Anirban Mukherjee | 2022-09-25 | 2022-10-01 | 6 | 0%
1.2.2 | Week2 tasks recommendation | Anita Dash, Anirban Mukherjee, Venkata M Gudala |  |  | 0 | 0%
1.2.3 | Front End Fields Finalizaiton | Anita Dash, Anirban Mukherjee, Venkata M Gudala |  |  | 0 | 0%
1.2.4 | Login Page | Anirban Mukherjee, Venkata M Gudala |  |  | 0 | 0%
1.2.5 | Load product images from local drive / google drive / drop box | Allavarapu Pratyusha Anandini, Boppana Hemanth |  |  | 0 | 0%
1.2.6 | Input product features ( weight, gold/silver/diamond quality, certification etc) | Bhargav Praneeth Bade |  |  | 0 | 0%
1.2.7 | Sync user data with Google Drive, Dropbox, GitHub, GitLab, BitBucket ( https://www.overleaf.com/blog/195-new-collaborate-online-and-offline-with-overleaf-and-git-beta ) | Jyothi Kalidindi, Manav Kataria, Niharika Pandey |  |  | 0 | 0%
1.2.8 | Usage Analytics | Panthula B SreeHarsha, Pramodh Kumar M |  |  | 0 | 0%
1.2.9 | Payment Module ( https://www.overleaf.com/user/subscription/plans ) | s.yogesh, Sai Prusni Bandela, Sriilalit Narayana , Venkata Rama Chintalapati |  |  | 0 | 0%
1.2.10 | User usage logs | Syed Mohammad Raza Zaidi, Tavish Bhandari |  |  | 0 | 0%
1.2.11 | Shipping Details | Thanuj Banala, Sangeeta Dharwal |  |  | 0 | 0%
1.2.12 | Front End Documentation | Polagani srinath, Utsav Ghosh |  |  | 0 | 0%
1.2.13 | Analyse existing eCommerce app from frontend features & technolgies point of view https://github.com/bssoft82/gl-retail-ordering-system | Sangeeta Dharwal, S. Ankita, R Shiny Jane |  |  | 0 | 0%
1.2.14 | Expected features from AWS and cost | Ashutosh Karol |  |  | 0 | 0%
1.2.15 | Test use cases and tests | R Shiny Jane, Sriilalit Narayana , Venkata Rama Chintalapati |  |  | 0 | 0%
1.2.16 | Bidding engine ( https://www.b4traders.com/) | Sriilalit Narayana , Venkata Rama Chintalapati |  |  | 0 | 0%
1.2.17 | Product tracking page | uttham kamarsu , V UDAYA KALYAN |  |  | 0 | 0%
1.2.18 | Buyer/Seller credentials page ( sensitive data to be masked and to be revealed only to right seller/buyer) | uttham kamarsu , V UDAYA KALYAN |  |  | 0 | 0%
1.2.19 | Product category / list of all products based on price, design, age | Venkata M Gudala, Panthula B SreeHarsha, Pramodh Kumar M |  |  | 0 | 0%
1.2.20 | Product recommendation page | Anirban Mukherjee, Venkata M Gudala |  |  | 0 | 0%
1.2.21 | Buyer cart | Anirban Mukherjee, Venkata M Gudala |  |  | 0 | 0%
1.2.22 | Seller product uploading screen ( flipkart has interesting process to upload a product to sell ) | uttham kamarsu , V UDAYA KALYAN |  |  | 0 | 0%
1.2.23 | Minutes of Meetings - Documentation | Polagani srinath, Utsav Ghosh |  |  | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
1.3 | Backend |  |  |  | 6 | 0%
1.3.1. | Back End Architecture (HLD and LLD) | Jophy Joseph, Aakash Singh, ANJALI RANGARAJ MAHESH REDDY | 2022-09-25 | 2022-10-01 | 6 | 0%
1.3.2 | Week2 tasks recommendation | Jophy Joseph, Anurag Singh |  |  | 0 | 0%
1.3.3. | Database fields finalization | Asadullah Adnan, Harsha Udutha, loks |  |  | 0 | 0%
1.3.4. | Database design | Aakash Singh, Apoorv Mehrotra, Rama krishna Movva |  |  | 0 | 0%
1.3.5 | Backend Documentation | Vaishnavi Deshay, Asadullah Adnan |  |  | 0 | 0%
1.3.6 | Usage Analytics | Harsha Udutha, Shahana Begum |  |  | 0 | 0%
1.3.7 | Admin/User Table design (including different usage logs, payments, permissions, shares, submission, uploads, downloads, deletes etc) | loks, Meghna Havalgi, Neha.R |  |  | 0 | 0%
1.3.8 | Analyse existing eCommerce from backend features & technolgies point of view https://www.b4traders.com/ https://github.com/bssoft82/gl-retail-ordering-system | Jophy Joseph, Priyam Ghosh, Priyash Indurkhya |  |  | 0 | 0%
1.3.9 | Payment module backend logic ( https://www.b4traders.com/ ) | Renuka Jonnalagadda, Sarasa Chakravarthy, Shivank Singhal |  |  | 0 | 0%
1.3.10 | Sync with Google Drive, Dropbox, GitHub, GitLab, BitBucket ( https://www.overleaf.com/blog/195-new-collaborate-online-and-offline-with-overleaf-and-git-beta ) | Srikanth Gaddam, Subbadeep Chattoraj, Pranshu Yaduvanshi |  |  | 0 | 0%
1.3.11 | History logs | syama sundar cheruvu, Vibhu Yamdagni |  |  | 0 | 0%
1.3.12 | AI module to validate the originality of the products | Shahana Begum, Rohan Nandkishor Soni |  |  | 0 | 0%
1.3.13 | Web security | Rohan Nandkishor Soni, syama sundar cheruvu |  |  | 0 | 0%
1.3.14 | Expected features from AWS and cost | shaik shakeel pasha, Thandaka Bhavana |  |  | 0 | 0%
1.3.15 | Test use cases and tests | Sravan Kumar Voona, Srikanth Gaddam, Hrithik Aditya |  |  | 0 | 0%
1.3.16 | Minutes of Meetings - Documentation | Polagani srinath, Vaishnavi Deshay |  |  | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
1.4 | Deployment |  |  |  | 6 | 0%
1.4.1. | Deployment Architecture | Dipanwita Banerjee, Ramakrishna Paramatmuni |  |  | 0 | 0%
1.4.2 | Week2 tasks recommendation | Dipanwita Banerjee, Akshay Patidar |  |  | 0 | 0%
1.4.3 | Deployment Plan | Dipanwita Banerjee, Ramakrishna Paramatmuni, Akshay Patidar |  |  | 0 | 0%
14.4 | Github account activation | Koka JayaSree, Sai Abhishek Manchinella |  |  | 0 | 0%
1.4.5 | AWS account features identification and account activation. AWS account will be provided by Great Learning. Reach out to Suruchi once required account features identified | Rangadhama Sastry Nivarthi, Aditi Singh, Ajay Kumar Gumudavelly |  |  | 0 | 0%
1.4.6 | Analyse existing eCommerce from deployment features & technolgies point of view https://github.com/bssoft82/gl-retail-ordering-system | Ankur sharma, Somya Pande, Rasiq Hussain |  |  | 0 | 0%
1.4.7 | Expected features from AWS and cost | Koka JayaSree, Samarth Hegde, Nancy Awadhiya, Pradeep Garapati |  |  | 0 | 0%
1.4.8 | Deploy locally (in your laptop or desktop) the existing MVP https://github.com/bssoft82/gl-retail-ordering-system | Dipanwita Banerjee, Koka JayaSree, Swathi Racha, Sidhant Chawla, Chelli Sai Manohar, Sreevani M, Mohammed Mudassar Jameel, Pradeep Garapati, Santanu Sudhansu Sekhar, SuryaPrakash Sahal |  |  | 0 | 0%
1.4.8.1 | Give demo to the project team | Dipanwita Banerjee, Samarth Hegde, Murali Katta |  |  |  | 0%
1.4.9 | Deploy in the free AWS account, the existing MVP https://github.com/bssoft82/gl-retail-ordering-system | Chalapathi, Anshika Maurya, Murali Katta, Chandana Kokkonda, Nancy Awadhiya, Sai Abhishek Manchinella |  |  | 0 | 0%
1.4.10 | Deployment Documentation | Fahmaan Mohammed, Dr Ulaganathan Subramanian |  |  | 0 | 0%
1.4.11 | Test use cases and tests | D Mohammed Sohail, Dr Ulaganathan Subramanian, Gadde Sai Varun |  |  | 0 | 0%
1.4.12 | Minutes of Meetings - Documentation | Polagani srinath, Fahmaan Mohammed |  |  | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
2 | Week - 2 |  | 2022-10-02 | 2022-10-08 | 6
2.1 | Project Management |  |  |  | 6 | 0%
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
2.2 | Front End |  |  |  | 6 | 0%
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
2.3 | Backend |  |  |  | 6 | 0%
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
2.4 | Deployment |  |  |  | 6 | 0%
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
[5 empty] | 0 | 0% | bar: WEEK 2 Mo to WEEK 2 Su
3 | Week - 3 |  | 2022-10-09 | 2022-10-15 | 6
3.1 | Project Management |  |  |  | 6 | 0%
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
3.2 | Front End |  |  |  | 6 | 0%
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
3.3 | Backend |  |  |  | 6 | 0%
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
3.4 | Deployment |  |  |  | 6 | 0%
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
[5 empty] | 0 | 0% | bar: WEEK 3 Mo to WEEK 3 Su
4 | Week - 4 |  | 2022-10-16 | 2022-10-22 | 6
4.1 | Project Management |  |  |  | 6 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
4.2 | Frontend |  |  |  | 6 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
4.3 | Backend |  |  |  | 6 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
4.4 | Deployment |  |  |  | 6 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
0%
100%